Demeters Dark Ride – An Attraction

Production Meeting Minutes

Recorded on the First day of the Ninth Month of the year Two Thousand & Five

- Lisa gave out design plans & talked thru design & running of show. Starting from beginning of the ride.

- Tix will be purchased from BATS office (although we need to look into a back up plan in case this doesn’t work)

- Music outside & possibility of the chestnut man

- Rich will be running the bar at The Pitt but also it will be magical and part of ride.

- 4 guides per ride (28 people per ride) 40 minute show

- Labyrinth could go in different places – Lisa has outlined possibilities on drawings.  The chamber is also undecided on.

- We will need to find storage for the BATS chairs.

- Where does the milk cauldron go?

ala

- Wunderkabin (?) will be attraction based but done by individual artists. It needs to be simple & effective for audience interaction.  Those artists interested in contributing to the Wunderkabinet(?…how do you spell this???) will need a day for exploring or more & will probably need a separate meeting

tht

- Balbao to be workshopped w 2 actors. The actor & the costume will create the character.

- Possiblity of circus routine & a physical Bridge of Jests

lpl

- How will Sally be elevated?

- Fortune Cookies are expensive so need to look into alternatives

- Flour may no be the best to use as it can be explosive if there’s too much. Also it’s very fine.

- Need some kind of grain.

eie

- Need to start collecting Scientific equipment/apparatus to dress Madame D’Ott’s Room (Buffs Space) although not too much needed

- Rosie & Lisa to find out about Dome in Buffs space & whether it can be covered from above.

- We need access for those that are disabled.  Options include watching on TV below or carrying people upstairs if they want. Further discussion to be held with BATS.

- Access to toilets also could be an issue – possibility of blindfolding or screening off a path to the toilets.

qwq

- Sound may be triggered not only by techs but by guides

- AV could utilise suicide doors either in the labyrinth or the suicide doors.

- There will need to be a separate DVD player for each projector

- Workshop next weekend (9-11th Sept) in MTA space at Te Whaea…there will be much experimentation.

Regular production meetings will be held every Wednesday at Janet’s (Thank you!) starting at 10am sharp.