Demeters Dark Ride

Production Meeting Minutes

Wed 7th September

Y

Minutes

- Last week’s minutes tabled….seconded & then thirded by various members of those present.

Upcoming Workshop

- Fri 9th-Sun 11th @ MTA garage in Te Whaea

- Friday - setting up.

Saturday – Impro & Play with a range of things/ideas

Sunday – Formulate & Clear up/presentation of inventions/experiments etc ….& AN IMPROVISED RUN OF THE SHOW!

- We have van for pick up/drop off on Fri morning. Lisa, Rosie & Erin to meet at Circa at 9.30am

- Madeline to open up MTA space & meet people there

- AV/lights will try projecting on to smoke/cloud

- Janet to be Scribe & bring fabric

- Masking/black fabric needed – also purple curtains from BATS (Rosie) & flats from Circa (Lisa)

- Jeff has very kindly volunteered his basement for storage

- Gauze maybe from Taki Rua

- Everybody bring a torch

- Madeline to bring Cauldron for Dry Ice & Lisa a bowl

- Candles & Candle holders will be useful

- Black Light – Vernon @ WPAC.

General

- Parachutes – Rosie to look into, Helen will email contact

- Madeline & Lisa have been doing chemistry experiments at lab at Uni for Madame D’Ott…among experiments were liquid nitrogen & Detergent in Dry ice

- Actors will be brought into process soon

- Madeline to start scheduling actors & costume workshops

- Actors so far are David (on street), Barry (in Pitt) & Guides: jess, Marjorie + 2 others. Possibility of Kilda, Pipi(Balbao), Reece & sally

Sound

- Jeff to operate sound

- Doesn’t want to use speakers etc very much except for in the labyrinth

Costumes

- All good so far….madame D’ott is coming along nicely

- Lady Sybil & guides need to be sorted

- Also the empty frocks for the diorama need to be sorted. Where can they go?…they may be wasted sitting on a seat

Publicity & Marketing

- The first straight media release is out

- The Thaumatological Society stuff was read out on Nat Rad by Kim Hill

- This weeks minutes from T. Society have been sent out

- Media Launch is 3rd October

- Some publicity shots will be taken during workshop

- Sponsorship is proving difficult (and we all think Helen & Madeline have been doing a great job!)

- Publicity mtg will be held on Thursday night

Next meeting….Wed 14th Sept….same time same place