DDR Minutes 14th

W8BNMSWD

DDR Production Meeting

Wed 14th Sept

Present: Madeline, Helen, Lisa, Erin, Annie, Jeff, Janet, Rosie

Apologies: Emma, Carlos, Hannah

Last weeks minutes were read back by the duchess

General note that Lisa Maule formerly known as Asil Eluam has changed her name by deed poll to General Lumen Gob

# Puffery

Over the next week the Puffery Committee will be generating  more straight media releases with angles for different press to pick up on

Kilda

The designers

Madame & Annie (Kapiti News)

Lisa (Western News)

Island Bay crew (Cook Strait News)

It was suggested that the chemistry angle might be a good one. Maybe the Salient could do a piece on Joanna Wojuar.

Emma to email Joanna to see if this is ok

Over the next week Emma will be contacting people about their bioís

Poster & Fliers will cost $480 (yay!) through Thames Printing. 3000 oversized A2 posters & 2000 A6 fliers

Need to put a thank you in the programme for them

Poster design is coming along. Madeline had a discussion with Donna.

Central image of poster is black & white & lots of detail round edges in colour.

Helen to send Donna the logos in colour and little to fit in row along bottom

Central image will be able to be proofed but we wonít see whole poster till just before it gets printed.

Deadline to get poster to Thames is 23rd Sept & we can pick it up on Fri 30th.

Madame, Miss Carter & Duchess will check poster at eleventh hour before giving it to Thames

Lisa needs to see copy so that she can make flashing tie in.

# Media Launch

Emma will be organising w help from Lynne & Rosie & Erin will help on day with set up

Copy of Thaumaturgical Society minutes being sent as invite to media. Wed 28th is RSVP date.

The day will be scheduled a little something like this:

3-6pm Set up

6pm arrive

6.fifteen (my five still doesnít work!) official stuff/media packs given out

Jess will be preparing her street speil so possibility of her doing that at the launch - she will talk more about this with Madame & Miss Carter

A meeting will be held soon w Duchess, Emma & Madame - time & place to be decided

# Programmes, Comps & other things

The Chestnut seller is confirmed & heís happy to wear costume etc & also happy to have flashings round his cart. Will do all rides for season including preview

Programme has been stared - please send any acknowledgements to Emma who also has the comps list

Cast & Crew comps maybe need to be used on preview night & Thank you comps on opening night or first week - comps are still being thought through.

Helen will talk to Marama re preview & rehearsal & FOH

Guides will be used for 3 nights minimum. Rosie will co-ordinate guides

Wheelchair access still an issue. Rosie to talk to Bronwyn Bent about it

# Rehearsal Spaces

Island Bay Surf Club has been confirmed for Mondays all day, Wednesday’s 12-2 and sat till 12.

Rosie to find venues for every Sat 12-five (still not working) and Wed 2.30 till five (this is getting ridiculous, I need to get my keyboard fixed!)

Possible venues include St Cuthberts (although interruptions there), Tararua tramping club, Newtown Community Centre. Madeline to call Masonic lodge

# Timeline of Show

3 rides per night. 7pm, 8pm, 9pm

Before ride starts BATS box office will tell audience they need a safety warning & will try sell them ear plugs

See attached very detailed timeline of show, minute by minute by General Gob

# Budget

Still pretty tight

Ads & ride sponsors still being followed up

# Sound

Would like 12 vibrators for Balbao section

Helen to talk to Device about possibility of deal and also about blow up dolls

Jeff is looking for anything small & mechanical or electronic that ticks, has moving parts or vibrates

# Costume

Inflatable life size dolls possibly needed (Helen looking into it)

Guides need to wear blacks

Possibility that they have gloves on & white faces

Janet needs numbers of guides for costuming - Rosie to tell her as soon as she knows

Costume is also responsible for material in labyrinth. Just needs measurements

# Lighting/Set

Sheet of gib & wood offered by Clare O’Leary

Duchess also has lots of wood etc

# Workshop

Was great and very useful.

Janet has posted notes from workshop on website

There will be a meeting with Carlos on Wednesday re Peppers ghost

Publicity photos are still needed as many great shots were taken at workshop but probably not that suitable for media

# General

Chamber still needs to be resolved

Production side of things is well on the way so now Madeline will be starting to work with on the performance aspects

Madeline will also be going back to look at details & make sure that all the elements are present in the rides.

# Next meeting: Wednesday 21st