## timeline
Demeter's Dark Ride - An Attraction
| week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26 | week 27 | week 28
| 28 May-3June | 4-10 June | 11-17 June | 18-24 June | 25 June-1 July | 2-8 July | 9-15 July | 16-22 July | 23-29 July | 30July-5August | 6-12 August | 13-19 August | 20-26 August | 27August-2 Sept | 3-9 Sept | 10-16 Sept | 17-23 Sept | 24-30 Sept | 1-7 October | 8-14 Oct | 15-21 Oct | 21-28 Oct | 29Oct-4Nov | 5-11 Nov
| Planning |  |  |  | Writing/ dramaturgy Gathering of texts, chants, song for Vocal workshops | [5 empty] | Participatory Laboratory Tours- Electrical Soirees | [6 empty] | Rehearsals |  |  | Pack-in & rehearsals | season | season | Production & pack-out
Creative Meetings | sound | Set & lighting | costume |  | AV | Set & lighting | sound | costume | AV | sound |  | costume | Set & lighting | AV | Set & lighting; Monday 6th sound session | 10-11 - weekend experimental workshop; Monday 12th - Carlos' open studio | sound meeting; Sunday 18th - Carlos hands-on session; Monday 19th session at Happy | rehearsals; Monday 26th - session at Happy | rehearsals; creative presentation to BATS | rehearsals; Monday 10th - session at Happy | rehearsals
Production meetings | week 18: Thursday 1st 9.30am; week 19: Wed 7th 10am; week 20: Wed 14th 10am; week 21: Wed 21st 10am; week 22: Wed 28th 10am; week 23: Wed 5th 10am; week 24: Wed 12th 10am
Creative Workshops | week 7: Dreaming Day (12th); week 8: Route planning (18th, 23rd); week 9: Creative presentations (26th); week 14: technical experimentation workshops; week 15: technical experimentation workshops; week 16: Weekend sessions in artists' workshops - take turns to have whoever is available come & learn & help; week 21: Actors' workshops
AV | week 20: experimental filming; week 21: experimentation and spacial mockups; week 22: experimentation and spacial mockups; week 23: Filming/editing; week 24: complete audio visual material
Sound | week 10: Listening sessions (organised by Jeff); week 14: preparation for workshop madeline and Jeff; week 15: experimental voice/text/sound workshop (actors and singers); week 20: draft score demo; week 21: recording; week 22: recording; week 23: sound ready for rehearsals; week 24: rehearsing with sound & technician
Set, props, costumes & installations | week 8: design of route & attractions (23rd); week 13: drawings, plans & costings for design; week 14: planning pre-construction & installation; week 18: Props & costumes list finalised; week 19: sourcing of props, costumes & materials; week 20: construction of props & costumes; week 21: purchase of set; making costumes; week 22: all props ready; preparation of set items; costume fittings; week 23: preparation of set items; costumes for filming ready; final lighting plan & equipment list; pack-in meeting with BATS; week 24: costumes completed, set items ready for installation; LX cue synopsis; week 25: set installation; rigging lights; week 26: season; week 27: find solution for any items that will need storage; week 28: return or storage of everything
Actors/Singers | week 11: Decision on numbers of actors/singers required; week 12: final casting; week 15: Experimental Voice/Text/ Sound workshops (actors and singers); week 17: Meetings with Actors re Archetypal Wkshps; week 19: Madeline prepares her Conjuring Acts and scripts; week 20: Actors Workshops Archetypal Explorations; week 21: Actors workshops Text Improvsations; week 22: Dramaturgy and Text Finalised with Actors plus costume fittings; week 23: rehearsals; week 24: rehearsals; week 25: rehearsals
Marketing |  | appoint publicist |  |  | marketing plan and budget confirmed; 1st TS meeting notices (27th) | report on 1st TS meeting | appointment & briefing of poster designer |  | 2nd TS meeting notices (25th) | report on 2nd TS meeting |  |  | prepare Guano info | 29th - Guano deadline; 3rd TS meeting notices; other activity begins | report on 3rd meeting of TS | activity increases - conjuror appears | 19th - send invitations to Miss Carter's Revelation; 23 - poster design deadline | publicity photo shoot; artwork to printers - 26th; sign-off posters/flyers - 28; send reminder re Revelation; book newspaper & radio ads | 3rd - Miss Carter's Revelation - media launch; 4th - poster/flyer distribution; interviews arranged; artwork, copy etc for ads | 8th - interview on Radio Active; other media interviews; record radio ad | appearances, street performances, publicity stunts; advertising begins end of week | reviews; newspaper & radio ads | newspaper & radio ads
People's availability |  |  | Jeff away | Jeff away; Emma away 18-20 then busy; | Jeff away until 27; Emma busy; Carlos busy | Kilda away from 8th; Emma busy; Carlos busy; Lisa busy 5-9th; Stuart busy; Helen away 8-11 | Kilda away; Emma busy until 10th; Carlos busy; Stuart busy; Helen busy 11-15 | Kilda back 17th; Carlos busy; Stuart busy; Emma away 16-17 | Carlos busy; Annie busy; Lisa busy 23-26; Stuart busy; Madeline and Kilda busy 25 -29 | Lisa & Annie busy from 31st | Lisa & Anniebusy until 6th; Sally goes to Denmark on 9 August | Lisa busy 14-19; Louise away 13-28; Sally away | Sally away | Fishnet Prod week Mad & Kil busy 27 -31st Opens 31st, runs @ 9pm until 4th Sept & then 8,9,10th: Sally away | Fishnet; Sally back 6 Sept; Barry involved in Gryphon production from 5 to 18 Sept | Fishnet ends 10th; Barry at Gryphon (not every night) & busy 14th; Hannah busy 12-16 | Barry - pack-out at Gryphon, 18 Sept; Annie not available evenings 19-25th | Lisa away 21-27th; Erin may be available 26-27; Hannah away weekend of 30th Sept. kilda away 26-30 sept. | 5 October - Erin finishes WOW & is completely available for DDR | 9 Oct - Barry not available3-6pm |  |  | Annie not available on 29th | Helen away 5-6; Erin away from 8th
Barry:Evenings: Sept 1, 5, 6, 7, 14, and Oct 7. Day times: Sep 3 10am - 5pm, Sep 4 12.30pm - 5 pm, Sep 17 2.30pm - 5pm, Sep 18 10am - 2pm, 24 2pm - 5pm and 9 Oct 3pm - 6pm. Any time at all: between Sep 9 to 11 inclusive.

## availability
Availability
Hannah | works Saturdays; from 4th July works 8-3 on Tuesdays & Fridays; August - finishing design comp
Kilda | Mondays, Wednesdays, Thursdays between about 5 & 9; "Fishnet" rehearsals & season opening end of August
Barry | sound for Gryphon production 5-18 Sept (not nightly); busy on 14 Sept
Emma | Works 9-5 Mon-Fri
Carlos | work for another show in late August, & other work up to 20 Sept; but able to be flexible with his time for meetings etc
Lisa | availble all day on mondays, tuesday mornings, wed until 3pm sometimes longer, tursday morning and friday morning.
Janet | works Thurs-Fri, 10-5
Sally | Wed & Fri evenings, & Sunday afternoons - Roadworks; Red Mole performance in September
Madeline | Working on Fishnet before 31 August
Helen | surgery 28th september

## marketing
Draft Marketing Timeline - Demeter's Dark Ride
October
21 | Opening Night
15 | Street Performance/ Publicity Stunts
10… | Interviews (papers, radio etc…)
8 | Interview, 'Caffiene and Asprin'
4 | Poster/Flier distribution
Interviews arranged (papers, radio etc..)
3 | Press Release/Revelation
September
29 | All publicity photos finalised
28 | Send reminder about 'Revelation'
28 | Final sign off posters/fliers
26 | Artwork to printers
25 | Publicity photos taken
23 | Graphic Designer's Deadline
19 | Send Invites to 'Revelation'
10 | 'appearances' begin (of conjurer?)
6 | Send press report about 3rd meeting
5 | 3rd Meeting of Thaumaturgical Society
August
29 | Letters to editor start 'sightings'?
29 | Put up 3rd meeting notices
29 | Info for Guano due at Bats
2 | Send press report about 2rd meeting
1 | 2nd Meeting of Thaumaturgical Society
July
25 | Put up 2nd meeting notices
5 | Send press report about 1st meeting
4 | 1st meeting of Thaumaturgical Society
June
27 | Put up 1st meeting notices